## Table 1
USER ACCEPTANCE TESTING TEST CASE TEMPLATE
PROJECT NAME
STaRT (Simple Triage and Rapid Treatment) Application
TESTING START DATE TESTING START TIME
2022-11-17
TESTING END DATE TESTING END TIME
2022-11-19
NAME OF TESTER(S)
Farah Muttardy (Farah) Richard Ogniewski (Rich) Elie Tannouri (Elie)
TEST NO. | DESCRIPTION OF TASKS | STEPS TO EXECUTE | EXPECTED RESULTS | PASS | FAIL | DEFECT / COMMENTS / ADDITIONS | TESTER
LOGIN ADMINISTRATION AND SECURITY:
1 | Confirm that User is in admins dictionary | Run Python File in Terminal | Get a prompt to enter User | X |  |  | Elie
2 | Password for User is working | After user entered, key password | Password for User entered is verified | X |  |  | Elie
3 | Invalid User ID stops the program | Invalid User | Program stops after typing an invalid User | X |  |  | Elie
4 | Invalid Password stops the program | Invalid password | Program stops after typing an invalid password | X |  |  | Elie
5
TEST MAIN FUNCTION:
1 | Print message with user login | Once login/password verified, display welcome message and options to select from | Welcome message and User name display, as well as 4 options to choose, one of which is Exit | X |  |  | Elie
2 | Get a prompt asking the user what they want to do | A prompt after the 4 options | Prompt: What would you like to to? (Enter a number) | X |  |  | Elie
3 | Does each option execute the code branch assigned to it | Ability to select options 1,2,3 | Each option executes a different Def function | X |  |  | Elie
4 | Selection 4 ends the program | User enters 4 | The program ends | X |  |  | Elie
5 | Only valid options are accepted | Enter option 5 | Message: Valid Option not selected | X |  |  | Elie
TEST CATASTROPHE BRANCH CODE:
1 | Call function 'enterCatastrophes' | Select 2 from options | Enter Catastrophe name | X |  |  | Elie
2 | Check if record already exists | Type in a catastrophe that is already there in catastrophe dictionary | Message says that catastrophe record exist | X |  |  | Elie
3 | If record exists, append to it | Add a state | Print out of revised dictionary with new state | X |  |  | Elie
4 | If record does not exist, create new record | Catastrophe does not exist | Add catastrophe name and state, print results | X |  |  | Elie
5
TEST LOCATION BRANCH CODE:*
1 | Call function 'enterlocations' |  | Enter City name | X |  |  | Rich
2 | Check if record already exists |  | Message says that Location exists | X |  |  | Rich
3 | If record exists, append to it | Add a zipcode | Print out of revised dictionary with zipcode | X |  |  | Rich
4 | If record does not exist, create new record | Add new location | Add new location and zip code | X |  |  | Rich
5
TEST VOLUNTEER BRANCH CODE
1
2
3
4
5
FUTURE UAT CHANGE LOCATION (COUNTY)
1
2
3
4
5
GENERAL QUESTIONS / COMMENTS
* | Location is currently by city with zipcode. However, the team has discussed exploring using counties as FEMA and state emergency management agencies use county designations for declarations during mitigation, preparedness, response and recovery operations. -Rich

## UAT Checklist
UAT Checklist
The following checklist's purpose is to ensure that the appropriate steps have been taken to execute a user acceptance test (UAT), to wrap up the process and ensure proper documentation has been completed. Simply choose "Yes, No or N/A" as it applies to the UAT process in the organization. The criteria listed below may not apply to all organizations, however, if a column contains a "No" answer, it should be revisited.
Criteria | Completed?
IT Project Team Preparedness
Has the project team been made aware of its role in advising on changes to business processes and procedures?
Has the project team been made aware of its role in providing support for all testing issues and concerns?
Has the project team been made aware of its role in tracking and managing test problems?
Has the project team been made aware of its role in changing system functionality?
UAT Team Preparedness
Has the UAT team been defined?
Does the UAT team understand its responsibility in executing the test cases and ensuring that the final outcomes of the tests are satisfactory?
Has the UAT team been told about its role and responsibility in ensuring that all test case input sources and output results are documented and auditable?
Has the UAT team agreed that the test cases provides comprehensive and effective coverage of all aspects of functionality of the application?
Has the UAT team been told about its role in documenting problems and working with the project team to resolve problems identified during testing?
Does the UAT team agree upon and understand the range of severity levels discussed with the project team and project stakeholders?
Does the UAT team understand the responsibilities and required actions for each category of problem identified during testing?
Does the UAT team understand that it must sign off on all test cases by signing the completed test scripts?
Has the UAT team been made aware of its role in accepting the results on behalf of the relevant user population?
Does the UAT team understand that it must recognize any changes necessary to existing processes and take a lead role in ensuring that the changes are made and communicated to other users?
Does the UAT team understand its role in confirming use of the system in performing business processes?
Does the UAT team understand its role in verifying performance on business critical functions?
Does the UAT team understand its role in confirming the integrity of data?
Does the UAT team understand its role in assessing system final production readiness?
Test Preparation
Has the plan for acceptance testing been completed and approved if required?
Have all possible system functions been described?
Is all input data available that is required for testing?
Has acceptance criteria be defined on which the completion of the acceptance test will be judged?
Have all user specific constraints been considered?
Has the testing procedure been defined?
Have test cases been created to discover contradictions between the software product and the requirements?
Have test cases been created to review whether timing constraints are met by the system?
Test Execution and Evaluation
Were all steps of the test run documented?
Was the acceptance test performed according to the test plan?
Did the users review the test results?
Are the services provided by the system in compliance with user requirements?
Were all defect documented?
Were all identified defects and issues resolved?
Did the users judge acceptability in accordance with the predetermined criteria?
Did each user sign off on output?
Yes
No
N/A